## Sheet1
Date | Project Name | Name | Employee ID | Completed Yesterday | Plan Today | Blockers | Summary
2025-08-25 17:05:00 | Hire-finch | Heisenberg | TECH1 | Explored how embeddings work with small datasets, tested similarity search for text comparison, and reviewed hierarchies and code. | Build a simple chatbot that uses embedding for context-aware answer and try to integrate the Pinecone web search and sync with mic. | Facing issue with the vector database setup, it's not connecting properly. | Heisenberg explored embeddings and similarity searches yesterday. Today, he plans to build a chatbot and integrate it with Pinecone and Supabase, but is facing issues with the vector database setup.
2025-08-25 17:05:00 | Hire-finch | Jessy | TECH2 | Set up the base structure for the AIS Chromehoster POC and explored how to capture Google Meet captions and mic access. | Build the conversation flow with daily standard and integrate the bot with the backend for shorting update. Prepare a demo flow for initial testing with dummy data. | Needs clarity on Meet bot authentication and guidance on scaling the caption storage efficiently. | Jessy set up the base structure for a POC and explored Google Meet features yesterday. Today, he plans to build a conversation flow and prepare a demo, but needs clarity on Meet bot authentication and efficient caption storage.
2025-08-25 17:09:23 | Hire-finch | Heisenberg | TECH1 | Completed building a simple chatbot that uses embedding for context-aware answer and integrated the pinecone web search and sync with mic | Identify which members are speaking to the AI and how to find the users for that |  | Heisenberg completed building a chatbot and will work on identifying speakers and finding unique user signatures today
2025-08-25 17:09:23 | Hire-finch | Jessy | TECH2 | Completed the integration of bot, but needs to work on the conversation flow | Work on the conversation flow |  | Jessy completed the bot integration and will work on the conversation flow today
2025-08-25 17:36:19 | Hire-finch | Heisenberg | TECH1 | Completed the UI integration into my project and worked on some bug fixes | Identify which user can speak in the meet and how it will be identified by the bot |  | Heisenberg completed the UI integration and bug fixes yesterday, and plans to work on user identification in meetings today without any blockers
2025-08-25 17:39:03 | Hire-finch | Heisenberg | TECH1 | Not specified | Not specified | Technical setup issues | Heisenberg did not specify what was completed yesterday or planned for today, but mentioned technical setup issues as blockers